## WBS
Plant Pals WBS Spreadsheet
Milestone | ID | Task | Owner | Duration (days) | Notes
Establish plant delivery and logistics plan | 1.1 | Source packaging materials | Fullfilment Director | 20 | The Fulfillment Director sources materials
| 1.2 | Hire delivery drivers | Human Resources Specialist | 10 | The Human Resource Specialist oversees hiring
| 1.3 | Calculate delivery fees | Financial Analyst | 2 | The Financial Analyst tracks costs and revenue
Select and install supply chain software and equipment | 2.1 | Supervise vendor setup of inventory management and fulfillment software | Inventory Manager | 5 | The Inventory Manager maintains inventory and oversees software installation
| 2.2 | Supervise vendor installation of the fulfillment equipment | Fulfillment Director | 5 | The Fulfillment Director ensures equipment is functional with the help of the Quality Assurance Tester
| 2.3 | Establish internal safety protocols for equipment | The Quality Assurance Tester | 2 | The Quality Assurance Tester ensures product quality and determines safety protocols and best practices
Develop and launch employee training program | 3.1 | Develop training sessions | Human Resources Specialist | 2 | The Human Resources Specialist develops the training sessions with the help of the Training Manager
| 3.2 | Train employees to use the software and equipment | Training Manager | 5 | The Training Manager runs the training program on the established protocols
| 3.3 | Monitor progress and improve training processes | Training Manager | 14 | The Training Manager refines training processes